## Instructions
INVESTMENT DECISION / BUSINESS CASE TEMPLATE
CapEx Investment Analysis ¦ Version 1.0
HOW TO USE THIS TEMPLATE
Step 1 | Go to the ASSUMPTIONS sheet and fill in all blue cells with your project data.
Step 2 | Review the CapEx & Depreciation schedule – add line items for each investment.
Step 3 | The P&L Impact and Cash Flow sheets calculate automatically.
Step 4 | NPV & IRR, Payback, Scenarios and Sensitivity update from your assumptions.
Step 5 | Use the PowerPoint deck to present the business case to decision-makers.
COLOR CODING GUIDE
Blue text | Hardcoded input – enter your numbers here
Black text | Formula / calculated value – do not overwrite
Green text | Link from another sheet – do not overwrite
Yellow fill | Key assumption – review before submitting

## Charts
FINANCIAL OUTPUT CHARTS
Chart 1 – Annual Free Cash Flow (TSEK) | [8 empty] | Chart 3 – NPV Sensitivity: Discount Rate vs. Revenue Growth
Chart 2 – Cumulative Free Cash Flow & Payback (TSEK) | [8 empty] | Chart 4 – Scenario Comparison: Key Metrics
Year | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034
Annual FCF (TSEK)
Cumulative FCF (TSEK)
NPV Sensitivity — Discount Rate (rows) × Revenue Growth (cols)
Disc Rate \ Rev Growth → | 2% | 3% | 4% | 5% | 6% | 7% | 8%
7% | 8687 | 9177 | 9692 | 10233 | 10802 | 11400 | 12029
8% | 7970 | 8428 | 8910 | 9417 | 9949 | 10507 | 11095
9% | 7302 | 7731 | 8183 | 8657 | 9155 | 9677 | 10226
10% | 6678 | 7081 | 7504 | 7949 | 8415 | 8905 | 9419
11% | 6096 | 6474 | 6871 | 7288 | 7726 | 8185 | 8666
12% | 5551 | 5907 | 6280 | 6671 | 7082 | 7513 | 7964
13% | 5041 | 5376 | 5727 | 6095 | 6480 | 6885 | 7309
Scenario Comparison
Metric | Downside | Base Case | Upside
NPV (TSEK) | -1200 | 3800 | 8500
IRR (%) | 5 | 14 | 22
Payback (yrs) | 9 | 5 | 3
10yr FCF (TSEK) | 500 | 9200 | 18000

## Assumptions
ASSUMPTIONS & PROJECT PARAMETERS
PROJECT INFORMATION
Project Name | [Enter project name]
Project Sponsor | [Name / Title]
Prepared by | [Name]
Date | [DD-MMM-YYYY]
Investment Category | CapEx
Investment Start Year | 2025
Analysis Period (years) | 10
Currency | SEK
Units | Thousands (TSEK)
CAPITAL EXPENDITURE (TSEK)
CapEx Item | Year 1 | Year 2 | Year 3 | Useful Life (yrs) | Residual Value (%)
Equipment / Machinery | 5000 | 0 | 0 | 10 | 10
Installation & Commissioning | 500 | 0 | 0 | 5 | 0
IT Systems & Software | 300 | 100 | 0 | 3 | 0
Civil Works / Facility | 1000 | 0 | 0 | 20 | 10
Other CapEx | 200 | 0 | 0 | 5 | 0
Total CapEx
REVENUE & COST ASSUMPTIONS
Parameter | Base Case | Unit | Notes
Annual Revenue Uplift (Yr 1) | 2000 | TSEK | Net additional revenue from investment
Revenue Growth Rate (Yr 2+) | 5% | % | Annual growth rate
Annual Cost Savings (Yr 1) | 800 | TSEK | Direct cost savings
Cost Savings Growth Rate | 3% | % | Annual growth in savings
Operating Cost Increase (Yr 1) | 300 | TSEK | Additional opex from investment
Opex Growth Rate | 3% | % | Annual growth in opex
Corporate Tax Rate | 22% | % | Effective tax rate
Discount Rate (WACC) | 10% | % | Weighted average cost of capital
Inflation Rate | 2% | % | General inflation assumption

## CapEx & Depreciation
CAPEX SCHEDULE & STRAIGHT-LINE DEPRECIATION
Item | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | Total
CAPITAL EXPENDITURE OUTFLOWS (TSEK)
Equipment / Machinery |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Installation & Commissioning |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
IT Systems & Software |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil Works / Facility |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other CapEx |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total CapEx
STRAIGHT-LINE DEPRECIATION (TSEK)
Depreciation – Equipment / Machinery | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450
Depreciation – Installation & Commissioning | 100 | 100 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0
Depreciation – IT Systems & Software | 133.3 | 133.3 | 133.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Depreciation – Civil Works / Facility | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
Depreciation – Other CapEx | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0
Total Depreciation

## P&L & Cash Flow
P&L IMPACT & FREE CASH FLOW ANALYSIS (TSEK)
Line Item | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034
REVENUE & SAVINGS
Revenue Uplift
Cost Savings
Gross Benefit
COSTS
Additional OpEx
Depreciation
EBIT (Incremental)
Tax on EBIT
NOPAT (Net Operating Profit After Tax)
CASH FLOW
CapEx Outflow (negative)
Add back: Depreciation
Free Cash Flow (FCF)
Cumulative FCF

## NPV & IRR
NPV & IRR ANALYSIS
DISCOUNTED CASH FLOW SUMMARY
Year | FCF (TSEK) | Discount Factor | PV of FCF (TSEK) | Cumulative PV
2025
2026
2027
2028
2029
2030
2031
2032
2033
2034
KEY METRICS
NPV (TSEK)
IRR (annual)
Discount Rate
Investment Horizon | 10 years

## Payback Period
PAYBACK PERIOD ANALYSIS
SIMPLE & DISCOUNTED PAYBACK
Year | FCF | Cum. FCF | PV of FCF | Cum. PV FCF | Payback?
2025
2026
2027
2028
2029
2030
2031
2032
2033
2034
PAYBACK SUMMARY
Simple Payback Period
Discounted Payback Period

## Scenario Analysis
SCENARIO ANALYSIS — BASE / UPSIDE / DOWNSIDE
SCENARIO ASSUMPTIONS
Parameter | Base Case | Upside | Downside | Unit | Notes
Revenue Uplift Yr 1 (TSEK) | 2000 | 2600 | 1400 | TSEK | Upside +30%, Downside -30%
Revenue Growth Rate | 5% | 8% | 2% | % | Annual growth in revenue uplift
Cost Savings Yr 1 (TSEK) | 800 | 1000 | 600 | TSEK | Upside +25%, Downside -25%
Cost Savings Growth | 3% | 4% | 1% | %
Additional OpEx Yr 1 (TSEK) | 300 | 250 | 400 | TSEK | Upside = lower costs
Discount Rate (WACC) | 10% | 9% | 12% | % | Risk adjusted
Total CapEx (TSEK) | 7000 | 6500 | 8500 | TSEK | Upside = cost savings
SCENARIO RESULTS SUMMARY
Metric | Base Case | Upside | Downside
NPV (TSEK)
IRR
Simple Payback (yrs)
10-Year Cumulative FCF
Year 1 FCF

## Sensitivity Analysis
SENSITIVITY ANALYSIS — NPV vs KEY DRIVERS
TABLE 1: NPV (TSEK) — Discount Rate × Revenue Growth Rate
Discount Rate \ Revenue Growth | 2% | 3% | 4% | 5% | 6% | 7% | 8%
7% | 9037 | 9527 | 10042 | 10583 | 11152 | 11750 | 12379
8% | 8298 | 8756 | 9238 | 9744 | 10276 | 10835 | 11422
9% | 7609 | 8039 | 8490 | 8964 | 9462 | 9985 | 10534
10% | 6966 | 7370 | 7793 | 8237 | 8703 | 9193 | 9707
11% | 6367 | 6745 | 7142 | 7559 | 7996 | 8455 | 8937
12% | 5806 | 6162 | 6535 | 6926 | 7337 | 7767 | 8219
13% | 5281 | 5616 | 5967 | 6334 | 6720 | 7125 | 7549
TABLE 2: NPV (TSEK) — Total CapEx × Year 1 Revenue Uplift
CapEx (TSEK) \ Revenue Yr 1 | 1000 | 1400 | 1700 | 2000 | 2400 | 2800 | 3200
5000 | 4096 | 6417 | 8158 | 9899 | 12220 | 14542 | 16863
6000 | 3218 | 5539 | 7280 | 9021 | 11342 | 13663 | 15984
7000 | 2339 | 4661 | 6401 | 8142 | 10464 | 12785 | 15106
8000 | 1461 | 3782 | 5523 | 7264 | 9585 | 11907 | 14228
9000 | 583 | 2904 | 4645 | 6386 | 8707 | 11028 | 13349
10000 | -296 | 2026 | 3766 | 5507 | 7829 | 10150 | 12471
11000 | -1174 | 1147 | 2888 | 4629 | 6950 | 9271 | 11593
LEGEND
Positive NPV (value creating) |  | Base case assumption |  | Negative NPV (value destroying)

## License (hidden)
CFO Eyes – License Terms (v1.0)
Copyright © CFO Eyes. All rights reserved.
This file is licensed to the original purchaser for a single user / single company under a non-transferable, non-exclusive license for internal use only. You may adapt and use the file internally without limit.
You may NOT:
- Resell, sublicense, share, publish, or otherwise distribute this file (original or modified) to third parties
- Post the file on public repositories, file-sharing services, or learning platforms
- Use the file to create competing templates for redistribution
A team / multi-company license is available — contact fredrik@cfoeyes.com.
Files are watermarked and redistribution can be traced. Violation may result in legal action.
Disclaimer: Provided for informational and illustrative purposes only. Not financial, legal, or professional advice.